## Signatures
AcouticAnalogies.jl
NPR 7150.2C Class E Compliance Matrix
National Aeronautics and
Space Administration
|  | Date: | xx/xx/2021
Prepared By:
<Name>
<Title>
NASA Glenn Research Center
Approved By:
Lisa VanderAar
GRC Software Technical Authority
NASA Glenn Research Center
Timothy Gaydos
GRC Software Assurance Technical Authority
NASA Glenn Research Center
Frank Dodd
GRC CIO Technical Authority
NASA Glenn Research Center

## Class E
NPR 7150.2C Compliance Matrix - Class E Software
AcousticAnalogies.jl
Class E Tailoring Compliance
Section | SWE # | Requirement Text | A-E Authority | Comply? FC - Fully Compliant, T - Tailored, N/A - Not Applicable | Compliance Evidence / Location | Tailoring Description | Tailoring Rationale
3 |  | Software Management Requirements
3.1 |  | Software Life Cycle Planning
3.1.2 | 33 | The project manager shall assess options for software acquisition versus development. | Center | FC | Software with necessary functionality does not already exist.
3.1.3 | 13 | The project manager shall develop, maintain, and execute software plans that cover the entire software life cycle and, as a minimum, address the requirements of this directive with approved tailoring. | Center | FC | Software Documentation can be found at github.com/dingraha/AcousticAnalogies.jl
3.1.10 | 42 | The project manager shall require the software developer(s) to provide NASA with electronic access to the source code developed for the project in a modifiable format. | Center | FC | Source code can be found at github.com/dingraha/AcousticAnalogies.jl
3.1.11 | 139 | The project manager shall comply with the requirements in this NPR that are marked with an ”X” in Appendix C consistent with their software classification. | Center | FC | Compliance information documented in this matrix.
3.1.12 | 121 | Where approved, the project manager shall document and reflect the tailored requirement in the plans or procedures controlling the development, acquisition, and deployment of the affected software. | Center | FC | Software Documentation can be found at github.com/dingraha/AcousticAnalogies.jl
3.1.13 | 125 | Each project manager with software components shall maintain a requirements mapping matrix or multiple requirements mapping matrices against requirements in this NPR, including those delegated to other parties or accomplished by contract vehicles or Space Act Agreements. | Center | FC | This matrix covers all software associated with this effort.
3.5 |  | Software Classification Assessments
3.5.1 | 20 | The project manager shall classify each system and subsystem containing software in accordance with the highest applicable software classification definitions for Classes A, B, C, D, E, and F software in Appendix D. | Center | FC | This software was developed to explore a design concept or hypothesis but not used to make decisions for an operational Class A, B, or C system or to-be-built Class A, B, or C system. It was therefore classified as class E.
3.5.2 | 176 | The project manager shall maintain records of each software classification determination, each software Requirements Mapping Matrix, and the results of each software independent classification assessments for the life of the project. | Center | FC | This matrix is stored alongside the source code at github.com/dingraha/AcousticAnalogies.jl
3.6 |  | Software Assurance and Software Independent Verification & Validation
3.6.1 | 22 | The project manager shall plan and implement software assurance per NASA-STD-8739.8. | Center | FC | See NASA-STD-8739.8A compliance matrix at github.com/dingraha/AcousticAnalogies.jl.
3.7 |  | Safety-critical Software
3.7.1 | 205 | The project manager, in conjunction with the SMA organization, shall determine if each software component is considered to be safety-critical per the criteria defined in NASA-STD-8739.8. | Center | FC | Software is not safety-critical.
3.1 |  | Software Reuse
3.10.2 | 148 | The project manager shall evaluate software for potential reuse by other projects across NASA and contribute reuse candidates to the NASA Internal Sharing and Reuse Software systems. However, if the project manager is a contractor, then a civil servant must pre-approve all such software contributions; all software contributions should include, at a minimum, the following information: | Center | FC | Software will be released through NASA software release process.
a. Software Title.
b. Software Description.
c. The Civil Servant Software Technical Point of Contact for the software product.
d. The language or languages used to develop the software.
e. Any third party code contained therein and the record of the requisite license or permission received from the third party permitting the Government’s use, if applicable.
3.11 |  | Software Cybersecurity
3.11.2 | 156 | The project manager shall perform a software cybersecurity assessment on the software components per the Agency security policies and the project requirements, including risks posed by the use of COTS, GOTS, MOTS, OSS, or reused software components. | Center and Center CIO | FC | Software is a stand-alone application that does not have the ability to communicate over the network.
3.11.6 | 155 | The project manager shall address identified cybersecurity vulnerabilities and weaknesses. | Center and Center CIO | N/A | No vulnerabilities or weaknesses identified.